Project: EU Asia-Link CALIBRE: Cambodia and Laos Initiative for Building Human Resources for the Environment 

Reference: KH/Asia-Link/04 142-966 

Document: WORKSHOP 1: AGREED POINTS & ACTIONS;     Version: Draft 0.1 /  Date: 30 May 2008
File Ref: 142966_W1_ACTIONS_D01

CALIBRE

European Union Funded Asia-Link Project

“Cambodia And Lao Initiative 
for Building human Resources for the Environment”

KH/Asia-Link/04 (142966)

WORKSHOP 1: AGREED POINTS & ACTIONS
Version  Draft 0.1
30 May 2008
	Prepared by
	David Polya
	University of Manchester
	UK

	Drafting History
	VER: D0.1
	DATE:  30 May 2008
	

	
	VER:
	DATE:
	

	
	VER:
	DATE:
	

	
	VER:
	DATE:
	

	
	
	
	

	Dissemination Level
	PU: Public
	

	
	PP: Restricted to other programme participants
 (including the Commission Services)
	

	
	RR: Restricted to a group specified by the Consortium (including the Commission Services)
	

	
	CO: Confidential, only for members of the Consortium (including the Commission services)
	√

	
	
	
	

	Verification & Approval
	Coordinator
	DATE: 30 May 2008
	

	
	Partners
	DATE: 
	

	
	
	
	

	Deliverable
	Reference/Name
	
	

	
	Due
	DATE:
	

	
	Completed & Submitted
	DATE:
	


This document has been produced with the financial assistance of the European Union. The contents of this document are the sole responsibility of The University of Manchester and can under no circumstances be regarded as reflecting the position of the European Union.
Agreed Points and Actions arising from the Kick-Off/Launch Meeting of the CALIBRE Project at Phnom Penh, May 7-10 2008.

	Meeting 

Ref.
	Point/

Action 

No.
	Point / Action
	Responsible
	Date 

Due

	W1
	1
	AGREED. The Project Management Committee will comprise the Team Leaders of the 4 Partner Institutions – University of Manchester (UNIMAN), Universite Joseph Fourier (UJF), National University of Laos (NUOL) and Royal University of Phnom Penh (RUPP) and any further members by invitation as is appropriate from time to time.
	N/A
	N/A

	
	2
	AGREED. The Team Leaders and Team Co-Leaders, who would delegate for the Team Leaders when the Team Leaders were unavailable, were agreed to be as follows:

UNIMAN Team Leader: David Polya

UJF Team Leader: Laurent Charlet

UJF Team co-Leader: Lorenzo Spadini

NUOL Team Leader: Lammai Phiphakhavong

NUOL Team Co-Leader: Bounthanh Bounvilay
RUPP Team Leader: Neth Barom

RUPP Team Co-Leader: Dany Va

UNN Team Leader: David Cooke

UNN Team Co-Leader: Samantha Jones

It was AGREED that the Team Leaders would be responsible for ensuring that their institution fulfilled their required responsibilities to the Project, including execution of agreed actions for which they were responsible.
	N/A
	N/A

	
	3
	AGREED. The role of University of Northumbria personnel, particularly David Cooke and Samantha Jones, was strongly welcomed. If deemed appropriate and practical, steps would be taken to formalize UNN’s involvement as a Partner unless their role as advisors / contractors was determined to be logistically more efficient. 
	N/A
	N/A

	
	4
	AGREED. Approximate dates for workshop should be revised as follows:
W1 (Kick-Off) Phnom Penh May 2008

W2 (QA) Manchester September 2008

W3 (Field) Vientianne & Laos January 2009

W4 (Remediation) Grenoble September 2009

W5 (Summary) Vientianne December 2010

With the W3 meeting to be timed to immediately pre or post date the proposed Chapman Conference to be held in Siem Reap in early 2009
	N/A
	N/A

	
	5
	AGREED. The following candidates forwarded by NUOL for research training in the European Union were approved for funding under the CALIBRE Project subject to acceptance by their host institutions:
Vilayth Vongdara (to UNIMAN for 1 year)

Sengathit Choulamany (to UNIMAN for 1 year)

Nhotkeo Phawadee (to UJF for 1 year)
	N/A
	N/A

	
	6
	AGREED. It was appropriate to consider supporting (i) research training not leading to a degree; (ii) research training leading, in part, towards a European PhD – this might for example involve a candidate studying at both UJF and UNIMAN; (iii) language training only where this was to support further research training. 
	N/A
	N/A

	
	7
	AGREED ACTION.  RUPP should forward suitable candidates for research training in UNIMAN (1 year) or UJF (2 years) by September 2008 and preferably considerably before that date.
	RUPP
	1st
Sept

2008

	
	8
	AGREED ACTION. Coordinator to request UJF Language Centre Information to be forwarded to NUOL and RUPP.
	UNIMAN
	23rd May

2008

	
	9
	AGREED ACTION. Partners to make suggestions to Coordinator regarding recommended or possible contractors to complete the reviews required under tasks 4 and 5.
	RUPP

NUOL

UJF

UNIMAN
	16th
May

2008

	
	10
	AGREED ACTION. Coordinator to distribute draft terms of reference for the reviews required under tasks 4 and 5. 
	UNIMAN
	23rd 

May

2008

	
	11
	AGREED ACTION. Lorenzo Spadini to email to RUPP and NUOL details of flow through cells and other equipment recommended to be purchased.
	UJF Spadini
	23rd
May 2008

	
	12
	AGREED ACTION. Coordinator to email draft template for project report to the Partners
	UNIMAN
	23rd May 2008

	
	13
	AGREED ACTION. Partners to email to the Coordinator suggestions for suitable International Advisors for the CALIBRE Project.
	RUPP
NUOL

UJF

UNIMAN
	23rd 
May 2008

and beyond

	
	14
	AGREED ACTION. Coordinator to invite appropriate personnel to act as International Advisors to the CALIBRE Project and advise Partners.
	UNIMAN
	23rd 

May 2008

and beyond

	
	15
	AGREED ACTION. Coordinator to complete Implementation Plan and distribute to members of the Project Management Committee for their comment and/or approval.
	UNIMAN
	23rd May 2008

	
	16
	AGREED ACTION. Coordinator to check requirement or otherwise for Team Leaders and Team Co-Leader to maintain timesheets and to notify Partners accordingly.
	UNIMAN
	23rd 

May 2008

	
	17
	AGREED ACTION. RUPP and NUOL to notify of Coordinator of details of any significant Asia-Link and other projects with potential links / overlaps / mutual interests with the CALIBRE Project
	RUPP Dany
NUOL

Bouthanh
	23rd 

May 2008

	
	18
	AGREED ACTION. RUPP and NUOL to notify the Coordinator of current status of video-conferencing facilities at the respective institutions.
	RUPP
NUOL
	23rd 

May 2008

	
	19
	AGREED ACTION. Coordinator to make arrangements for the establishment of a bespoke CALIBRE Project website.
	UNIMAN
	23rd 

May 2008

	
	20
	AGREED ACTION. Coordinator to circulate draft minutes and agreed points & actions to all Partners.
	UNIMAN
	23rd 

May 2008

	
	21
	AGREED ACTION. Coordinator to arrange for the drafting and distribution for approval.signing to the CALIBRE Project Partners of contracts between the Lead Beneficiary, The University of Manchester, and each of the other CALIBRE Project Partners to assure that the other CALIBRE Project Partners agree to the conditions in the Lead Contract as required by that Contract. Transfer of further funds from the Lead Beneficiary to the other CALIBRE Project Partners would be dependent upon appropriate accession of the Partners to the Lead Contract.
	UNIMAN
	13th 
June 

2008

	
	22
	AGREED. All RUPP personnel and in particular Dr Neth Barom, Ms Dany Va (Lead Organiser of the Workshop) and her team including Ms Chea Eliyan (as Master of Ceremonies) should be thanked for their thoroughly professional organization of the CALIBRE Kick-Off/Launch Meeting and should be thanked for their hospitality.
	N/A
	N/A


Matters Arising After the Kick-Off Meeting

[1] The Coordinator was heavily involved in compulsory jury service f or two weeks after his return to the UK from the Kick-Off/Launch meeting – this has unfortunately delayed the completion of a number of actions. June 13th  2008 is a suggested realistic revised date for the completion of all Actions previously agreed to be completed by May 23rd.

[2] The dates of the Chapman Conference organised by Lex Van Geen (Columbia University) and Scott Fendorf (Stanford University) and to be held in Siem Reap, Cambodia are now known to be March 23-29 2009 – the Project Management Committee may wish therefore to reconsider the timing of the 3rd Workshop in Vientianne & Laos – possibly to move it to March 2009 from January 2009.

[3] Correction. At the meeting the Coordinaotr indicated that there was funding available for 6 persons from each of NUOL and RUPP to travel from South-East Asia to Europe for the Workshops to be held in Manchester and in Grenoble. This is not correct. There is funding for 3 persons from each of NUOL and RUPP to travel to each of these workshops. However, further NUOL and RUPP personnel who are studying in Europe at the time of a workshop would obviously also be able to attend without the need for further international Asia-EU travel support.

[4] As a general point, it is noted that wherever there is an inconsistency between what is stated in Meetings or by Partners or Partner representatives and what is stated in the Contract between the European Commission and the Lead Beneficiary (University of Manchester) the Contract takes precedence.
If there any queries, please do not hesitate to contact me.

David Polya

Coordinator, CALIBRE

David.polya@manchester.ac.uk
+ 44 161 275 3818 (Phone)

+44 161 306 9361 (FAX)

30 May 2008 

Manchester, UK



























Page 1 of 5

